## Sheet1
Cost Baseline 1
Project Name: UOW Booking System Development | Date: 03/05/2021
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
Week
WBS Categories | 1 | 2 | 3 | 4 | 5 | Total Cost
1.Planning
1.1 Understanding the project scope and objectives | 207 |  |  |  |  | 207
1.2 Planning on cost,budgeting, schedule and list of deliverables | 225 |  |  |  |  | 225
1.3 Research on office location | 3635 |  |  |  |  | 3635
1.4 Assigning roles and tasks | 90 |  |  |  |  | 90
1.5 Purchasing of Project Resources | 7070 |  |  |  |  | 7070
2.Requirement
2.1 Creating Project Charter |  | 206 |  |  |  | 206
2.2 Obtain approval from CIO |  | 0 |  |  |  | 0
2.3 Finishing project deliverables |  | 183 |  |  |  | 183
3.Design
3.1 Research on the most optimal way to develop program |  |  | 305 |  |  | 305
3.2 Drafting the User Interface |  |  | 340 |  |  | 340
3.3 Research on the program requirements |  |  | 87 |  |  | 87
4.Development
4.1 Database Design |  |  | 207 |  |  | 207
4.2 Prototype Development |  |  | 33.6 | 67.4 |  | 101
5.Testing
5.1 Program Testing |  |  |  | 510 |  | 510
5.2 Program Debugging |  |  |  |  | 77 | 77
6.Presentation
6.1 Record Presentation |  |  |  |  | 510 | 510
6.2 Presentation submission |  |  |  |  | 0 | 0
7.Meeting
7.1 Kickoff Meeting | 54 |  |  |  |  | 54
7.2 Meeting 1 |  | 54 |  |  |  | 54
7.3 Meeting 2 |  |  | 54 |  |  | 54
7.4 Meeting 3 |  |  |  | 54 |  | 54
7.5 Meeting 4 |  |  |  | 54 |  | 54
7.6 Meeting 5 |  |  |  |  | 54 | 54
7.7 Meeting 6 |  |  |  |  | 54 | 54
Subtotal | [5 empty] | 14131
Reserves | [5 empty] | 24369
Total | [5 empty] | 38500
Assumptions