## Sheet1
Cost Baseline 2
Project Name: UOW Booking System Development | Date: 03/05/2021
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
Week
Week
WBS Categories | 1 | 2 | 3 | 4 | 5 | 6 | Total Cost
1.Planning
1.1 Understanding the project scope and objectives | 207 | [5 empty] | 207
1.2 Planning on cost,budgeting, schedule and list of deliverables | 225 | [5 empty] | 225
1.3 Research on office location | 3635 | [5 empty] | 3635
1.4 Assigning roles and tasks | 90 | [5 empty] | 90
1.5 Purchasing of Project Resources | 7070 | [5 empty] | 7070
2.Requirement
2.1 Creating Project Charter |  | 206 |  |  |  |  | 206
2.2 Obtain approval from CIO |  | 0 |  |  |  |  | 0
2.3 Finishing project deliverables |  | 183 |  |  |  |  | 183
3.Design
3.1 Research on the most optimal way to develop program |  |  | 305 |  |  |  | 305
3.2 Drafting the User Interface |  |  | 340 |  |  |  | 340
3.3 Research on the program requirements |  |  | 87 |  |  |  | 87
4.Development
4.1 Database Design |  |  | 207 |  |  |  | 207
4.2 Prototype Development |  |  | 33.6 | 67.4 |  |  | 101
4.3 Finished Program Prototype
5.Testing
5.1 Program Testing |  |  |  | 510 |  |  | 510
5.2 Program Debugging |  |  |  |  | 113 |  | 113
6.Presentation
6.1 Record Presentation |  |  |  |  | 255 | 255 | 510
6.2 Presentation submission |  |  |  |  | 0 |  | 0
7.Meeting
7.1 Kickoff Meeting | 54 | [5 empty] | 54
7.2 Meeting 1 |  | 54 |  |  |  |  | 54
7.3 Meeting 2 |  |  | 54 |  |  |  | 54
7.4 Meeting 3 |  |  |  | 54 |  |  | 54
7.5 Meeting 4 |  |  |  | 54 |  |  | 54
7.6 Meeting 5 |  |  |  |  | 54 |  | 54
7.7 Meeting 6 |  |  |  |  | 54 |  | 54
8.Change Request
8.1 Approval of Project Change Request Form
8.2 Development of Additional Prototype Feature |  |  |  | 215 |  |  | 215
Subtotal | [6 empty] | 14382
Reserves | [6 empty] | 24118
Total | [6 empty] | 38500