## Sheet1
Cost Estimate
Project Name: UOW Booking System Development | Date: 03/05/2021
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor (in hours) |  | $ Total | Labor |  | $ Total | Labor
1.Planning
1.1 Understanding the project scope and objectives | 12.8 | 15 | 192 |  |  |  | 192 | 15 | 207
1.2 Planning on cost,budgeting, schedule and list of deliverables | 10 | 20 | 200 |  |  |  | 200 | 25 | 225
1.3 Research on office location | 8 | 15 | 120 |  |  |  | 120 | 3515 | 3635
1.4 Assigning roles and tasks | 8 | 10 | 80 |  |  |  | 80 | 10 | 90
1.5 Purchasing of Project Resources | 6 | 10 | 60 |  |  |  | 60 | 7010 | 7070
2.Requirement | [8 empty] | 0
2.1 Creating Project Charter | 5.8667 | 30 | 176 |  |  |  | 176 | 30 | 206
2.2 Obtain approval from CIO | [8 empty] | 0
2.3 Finishing project deliverables | 11.2 | 15 | 168 |  |  |  | 168 | 15 | 183
3.Design | [8 empty] | 0
3.1 Research on the most optimal way to develop program | 11.2 | 25 | 280 |  |  |  | 280 | 25 | 305
3.2 Drafting the User Interface | 16 | 20 | 320 |  |  |  | 320 | 20 | 340
3.3 Research on the program requirements | 4.8 | 15 | 72 |  |  |  | 72 | 15 | 87
4.Development
4.1 Database Design | 12.8 | 15 | 192 |  |  |  | 192 | 15 | 207
4.2 Prototype Development | 19.2 | 5 | 96 |  |  |  | 96 | 5 | 101
5.Testing
5.1 Program Testing | 16 | 30 | 480 |  |  |  | 480 | 30 | 510
5.2 Program Debugging | 14.4 | 5 | 72 |  |  |  | 72 | 5 | 77
6.Presentation | [8 empty] | 0
6.1 Record Presentation | 80 | 6 | 480 |  |  |  | 480 | 30 | 510
6.2 Presentation submission
7.Meeting | 5.6 | 30 | 168 |  |  |  | 168 | 210 | 378
Subtotal | [8 empty] | 14131
Reserves | [8 empty] | 24369
Total | [8 empty] | 38500
Assumptions