## Kickoff Meeting
Issue Log
Date : 12/04/2021
Issue # | Issue Description | Impact on Project | Date Reported | Reported By | Assigned To | Priority(M/H/L) | Due Date | Status | Comments
1 | Making of Project Charter | Approval Needed to Continue Project | 2021-12-04 |  | Limo, Kenndy, Figo, Valerie, Pavi, Erick | H | 15/04/2021 | Resolved

## Meeting 3
Issue Log
Date : 04/05/2021
Issue # | Issue Description | Impact on Project | Date Reported | Reported By | Assigned To | Priority(M/H/L) | Due Date | Status | Comments
1 | Making of Project Charter | Approval Needed to Continue Project | 2021-12-04 |  | Limo, Kenndy, Figo, Valerie, Pavi, Erick | H | 15/04/2021 | Resolved
2 | Making of Update Change Request Form | Approval Needed to implement the changes | 2021-04-05 |  | Limo, Kenndy, Figo, Valerie, Pavi, Erick | H | 2021-06-05 | Resolved