## Meeting 1
Risk Register for Paradis UOW Booking System
2021-04-21
Project Name: UOW Booking System Development
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 2 | A new member joined. | HR | Ice breakers, team bonding activity. | Erick Chow | H | H | NIL - Team member has done ice breaker activities with other members.
2 | 1 | Scheduling meetings. | Communications | Improve the time-scheduling and each member should work harder to meet the with the team. | Erick Chow | L | M | L - Project Coordinator has coordinated with team to ensured meetings are scheduled properly

## Meeting 2
Risk Register for Paradis UOW Booking System
2021-05-03
Project Name: UOW Booking System Development
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 4 | A new member joined. | HR | Ice breakers, team bonding activity. | Erick Chow | H | H | NIL - Team member has done ice breaker activities with other members.
2 | 3 | Scheduling meetings. | Communications | Improve the time-scheduling and each member should work harder to meet the with the team. | Erick Chow | L | M | L - Project Coordinator has coordinated with team to ensured meetings are scheduled properly
3 | 1 | Unexpected bugs on prototype | Quality | Extensive debugging to find as many bugs as possible | Kenndy | L | H | M - Team has done extensive test cases to prevent errors
4 | 2 | Exceeding budget | Cost | Cutting costs, securing additional funding | Valerie | L | M | L - Team has been very careful with handling budget

## Meeting 3
Risk Register for Paradis UOW Booking System
2021-05-04
Project Name: UOW Booking System Development
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 7 | A new member joined. | HR | Ice breakers, team bonding activity. | Erick Chow | H | H | NIL - Team member has done ice breaker activities with other members.
2 | 6 | Scheduling meetings. | Communications | Improve the time-scheduling and each member should work harder to meet the with the team. | Erick Chow | L | M | L - Project Coordinator has coordinated with team to ensured meetings are scheduled properly
3 | 1 | Unexpected bugs on prototype | Quality | Extensive debugging to find as many bugs as possible | Kenndy | L | H | M - Team has done extensive test cases to prevent errors
4 | 4 | Exceeding budget | Cost | Cutting costs, securing additional funding | Valerie | L | M | L - Team has been very careful with handling budget
5 | 2 | Unexpected change to program requirement | Time, Scope | Immediately finalize program requirement with stakeholder and work on changes | Kenndy | M | M | L - Lead Developer has added the extra requirement in the shortest time
6 | 3 | Miscalculation on the project budget and schedule due to unforeseeable changes | Time,Budget | Directly determining the correct cost and time estimation needed | Limousine | M | M | nil - Team has correctly recalculated the resource needed to complete the project changes
7 | 5 | Miscommunication on the new program features | Communications, Stakeholder | Clarify with stakeholder as soon as possible if there are doubts on program requirement | Kenndy | L | M | L - Additional program requirement has been stated very clearly on theproject change request document